## Sheet1
Date: 161107
PHASE 5 2016 - 2017 | 161114 ILA is pending BOCC Approval at 12/14/16 Meeting; 161017 Selection of Vendor & Contract Submitted to Board for approval; 160919 RFP Submitted to Board for approval; 160822 Awaiting FDOT approval Central/US 1 hydrant; 160712 FDOT received package. | SUB DIVISION | FKAA APPROVED HYDRANT LOCATION | DATE TO ENGINEERING FOR DRAWINGS | ENGINEERING DRAWINGS COMPLETE | DATE TO FDOT FOR APPROVAL (If Required) | FDOT PERMIT APPROVAL | FKAA UTILITY PERMIT (Good for 1 year) | DATE TO CONTRACTOR FOR INSTALLA- TION | COMPLETE
16-01 | Central & US 1 … Feasible on US #1 - Permit still pending as of 10/12/17 | Hibiscus | Approved | 2016-04-16 | 2016-06-07 |  | FDOT APPROVED 11/02/16 | Application submitted Wk of 160627
16-02 | Largo Road & Big Pine Road … Place on Largo | Pamela Villa MM 102 Oceanside | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-03 | Largo Road & Bahia Honda Road … Place on Largo | Pamela Villa MM 102 Oceanside | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-04 | Largo Road & Vaca Road . . . Place on Vaca | Pamela Villa MM 102 Oceanside | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-05 | Cactus & Thomas Avenue Feasible 6" water main on both streets (Moved from Phase 4) | Rock Harbor | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-06 | Michelle & Judy (Moved from Phase 4) | Largo Gardens | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-07 | U.S. 1 & Lignumvitae Drive … Place in US #1 | Pamela Villa MM 102 Oceanside | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-08 | Mahogany & Oleander … Place on Mahogany | Pamela Villa MM 102 Oceanside | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-09 | Collins Street & Village Drive … Place on Collins | Angler's Park MM 103.4 Ocean | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-10 | Sound Drive & Plante Street … Place on Sound | Angler's Park MM 103.4 Ocean | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-11 | Snapper & Blue Runner l … Place on Snapper | Largo Sound Park MM 103.4 Ocean | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-12 | Kingfish & Se Marlin Ave … Place on Marlin | Largo Sound Park MM 103.4 Ocean | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-13 | Barracuda between Bluerunner and Turbot. Water main is on north lane (exit to US1). | Largo Sound Park MM 103.4 Ocean | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-14 | 672 Dolphin Avenue | Angler's Park MM 103.4 Ocean | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
16-15 | Largo Road & Grassy Rd (approved for Grassy) | Largo Sound Park MM 103.4 Ocean | Approved | 2016-04-16 | 2016-06-07 |  | N/A | Application submitted Wk of 160627
NEW PHASE 6 2017-2018 | THIS IS FY 17-18: 161114 None of the Phase 6 Fire Hydrants require FDOT approval; 160919 The hydrant list was submitted to FKAA to determine location feasibility. | SUB DIVISION | FKAA APPROVED HYDRANT LOCATION | DATE TO ENGINEERING FOR DRAWINGS | ENGINEERING DRAWINGS COMPLETE | DATE TO FDOT FOR APPROVAL (If Required) | FDOT PERMIT APPROVAL | FKAA UTILITY PERMIT (Good for 1 year) | DATE TO CONTRACTOR FOR INSTALLA- TION | COMPLETE
17-01 | Mangrove Lane (Inside Paradise Point)- Feasible | Paradise Point | Yes
17-02 | Mangrove Lane (Middle) Feasible | Paradise Point | Yes
17-03 | Mangrove Lane (Entrance to Paradise Point) Feasible | Paradise Point | Yes
17-04 | Lake Surprise & Plantation Road-Feasible on Lake Surprise Blvd & South side of Plantation Rd. Not feasible on North side of Plantation | Lake Surprise | Yes
17-05 | Plantation & Upper Matecumbe Road- Feasible on Both Streets | Lake Surprise | Yes
17-06 | Largo Road & Long Key Road (Beginning of road) Feasible on Both Streets | Lake Surprise | Yes
17-07 | Largo Road & Long Key Road (End of the road)- Not Feasible at end of Long Key Road-4” wm starts at Lots7 & 38/ Feasible anywhere south of those lots. | Lake Surprise | Yes
17-08 | Largo Road and Grassy Road Feasible on Largo Road & North side of Grassy Rd. Not feasible on South side of Grassy Road. | Lake Surprise | Yes
17-09 | Grassy Road (End of the street) Not Feasible at end of Grassy Road-4” wm starts at Lot 7 / Feasible anywhere south of that lot. | Lake Surprise | Yes
17-10 | Oakwood Avenue & Linda Drive Feasible on Both Streets | Largo Hi-Land | Yes
17-11 | Stillwright Way and North Drive (Corner) | Stillwright Point | Yes
17-12 | Blackwater Lane & Coral Way (Corner) Feasible on Blackwater. Not feasible on Coral. | Stillwright Point | Yes
17-13 | N. Blackwater Lane & Sexton Way Feasible on N Blackwater. Not feasible on Sexton Way. | Stillwright Point | Yes
17-14 | N. Blackwater Lane & South Drive Feasible on N Blackwater. Not feasible on South Drive. | Stillwright Point | Yes
17-15 | N. Blackwater Lane (about ½ down add a second hydrant street is so long) Feasible on N Blackwater. | Stillwright Point | Yes
DON'T PRINT BELOW LINE 37
Extra location if needed | Grassy Road & Swallow Road - Per Brian where the road intersects there is a hydrant about 300 feet away | Sexton Cove | this was 17-11 |  |  |  | IMPORTANT - Did Dave say to delete this hydrant?
Extra location if needed | North End (at the end) | Stillwright Point
Extra location if needed | South Drive (middle) | Stillwright Point
Extra location if needed | S. Blackwater In (End) | Stillwright Point
Extra location if needed | Paradise Drive & Coral Way | ?
Extra location if needed | Mockingbird Road | ?
Per Brian | Sexton Cove Drive & Sexton Cove Road | REMOVED from list INSTALLED
DO NOT PRINT BELOW THIS LINE
PHASE I 13-01 | Wheaton's | Near Key Largo Village | Yes |  |  |  | Expires within 120 days from commencement of work (Appv'd 07/08/14) | Thomas Approved 8/15/14 | LaRocco 7/29/14 | COMPLETE
13-02 | Wynken, Blynken & Nod | Wynken, Blynken & Nod | Yes | Complete | Complete | Complete | PERMIT EXPIRES 10/21/14 | Thomas Approved 8/15/14 | LaRocco 7/29/14 | COMPLETE
13-03 | St, Justin's Church | Near the church | Yes | Complete | Complete | Complete | PERMIT EXPIRES 10/14/14 | Thomas Approved 8/15/14 | LaRocco 7/29/14 | COMPLETE
13-04 | Harry Davis Circle | Near Newport Village | Yes | Complete | Complete | Complete | PERMIT EXPIRES 10/08/14 | Thomas Approved 8/15/14 | LaRocco 7/29/14 | COMPLETE
13-05 | Harborage | Near Harborage | Yes | Complete | Complete | Complete | PERMIT EXPIRES 10/21/14 | Thomas Approved 8/15/14 | LaRocco 7/29/14 | COMPLETE
13-06 | Bay Harbor | Near Bay Harbor Lodge | Yes | Complete | Complete | Complete | PERMIT EXPIRES 10/08/14 | Thomas Approved 8/15/14 | LaRocco 7/29/14 | COMPLETE
13-07 | Churchill Downs | Near Cross-Key Waterways | Yes | Complete | Complete | Complete | Expires within 120 days from commencent of work (Appv'd 07/07/14) | Thomas Approved 8/15/14 | LaRocco 7/29/14 | COMPLETE
13-08 | Hibiscus Lane/Freedom Park | Freedom Park | Yes | Complete | Complete | Complete |  | Thomas Approved 8/15/14 |  | COMPLETE
13-09 | Rowell's Marina | Rowell's Marina | Yes | Complete | Complete | FDOT N/A |  |  |  | COMPLETE
PHASE 2 2014 - 2015 | PHASE 2 is 100% COMPLETE
14-01 | Corner of SIR FRANCIS and Buccaneer | Pirate's Cove | Yes | Page 8 | Complete | Engr Drawing Complete | FDOT Not Required | Permit Expires 10/17/15 | To La Rocco on 5/11/15 | Complete
14-02 | End of JOLLY ROGER | Pirate's Cove | Yes | Page 9 | Complete | Engr Drawing Complete | FDOT Not Required | Permit Expires 10/17/15 | To La Rocco on 5/11/15 | COMPLETE - Inv. 072915
14-03 | Corner of GASPARILLA and Tortuga | Pirate's Cove | Yes | Page 10 | Complete | Engr Drawing Complete | FDOT Not Required | Permit Expires 10/17/15 | To La Rocco on 5/11/15 | COMPLETE
14-04 | ANNE BONNY | Pirate's Cove | Yes | Page 11 | Complete | Engr Drawing Complete | FDOT Not Required | Permit Expires 10/17/15 | To La Rocco on 5/11/15 | COMPLETE
14-05 | LONG BEN | Pirate's Cove | Yes | Page 12 | Complete | Engr Drawing Complete | FDOT Not Required | Permit Expires 10/17/15 | To La Rocco on 5/11/15 | COMPLETE - Inv. 072915
14-06 | PIRATES Drive & Buccaneer | Pirate's Cove | Yes | Page 13 | Complete | Engr Drawing Complete | FDOT Not Required | Permit Expires 10/17/15 | To La Rocco on 5/11/15 | COMPLETE - Inv. 072915
14-07 | GASPARILLA | Pirate's Cove | Yes | Page 14 | Complete | Engr Drawing Complete | FDOT Not Required | Permit Expires 10/17/15 | To La Rocco on 5/11/15 | COMPLETE - Inv. 072915
14-08 | JEAN Lafitte | Near Pirate's Cove | Yes | Page 15 | Complete | Engr Drawing Complete | FDOT Not Required | Permit Expires 10/17/15 | To La Rocco on 5/11/15 | COMPLETE - Inv. 072915
PHASE 3 2014 - 2015 | PHASE 3 COMPLETED 2/12/16 |  | 160427: The District received the Performance Bond; 03/18/15: La Rocco to forward Performance Bond & Certificate of Liability Insurance to the District; 02/23/15: The District approved the Contract with LaRocco.
14-09 | 2ND AVE AND EAST 2ND STREET REPLACE THE WELL WITH HYDRANT | Mandalay | Yes | Page 2 08/20/15 | Complete | Not Req'd | Replaces Tradewinds | Permit Expires 11/9/16 | To La Rocco on 11/9/15 | COMPLETE
14-10 | EAST FIRST STREET AND EAST FIRST AVE CENTER | Mandalay | Yes | Page 3 08/20/15 | Complete | Not Req'd | Replaces Tarpon Basin | Permit Expires 11/9/16 | To La Rocco on 11/9/15 | COMPLETE
14-11 | Corner of KINGFISH & JEWFISH Avenue | Largo Sound | Yes | Page 1 | Complete | Not Req'd |  | Permit Expires 11/9/16 | To La Rocco on 11/9/15 | COMPLETE
14-12 | Corner of AVENUE A & 3rd Road in Largo Sound | Largo Sound | Yes | Page 2 | Complete | Not Req'd |  | Permit Expires 11/9/16 | To La Rocco on 11/9/15 | COMPLETE
14-13 | Off Bowen Drive down BISCAYNE ROAD | Rivera Village | Yes | Page 4 | Complete | Not Req'd |  | Permit Expires 11/9/16 | To La Rocco on 11/9/15 | COMPLETE
14-14 | Garden Cove Drive and CAYMAN LANE | Garden Cove | Yes | Page 6 | Complete | Not Req'd |  | Permit Expires 11/9/16 | To La Rocco on 11/9/15 | COMPLETE
14-15 | ROSE STREET AND THOMAS AVE | Rock Harbor | Yes | Page 4 08/20/15 | Complete | Not Req'd | Replaces Sexton Cove | Permit Expires 11/9/16 | To La Rocco on 11/9/15 | COMPLETE
14-16 | Corner of TAYLOR DRIVE at the Curve in the Road | Taylor Creek | Yes | Page 3 | Complete | Not Req'd |  | Permit Expires 11/9/16 | To La Rocco on 11/9/15 | COMPLETE
PHASE 5 2015 - 2016 | HYDRANT LOCATION | SUB DIVISION | FKAA APPROVED HYDRANT LOCATION | DATE TO ENGINEERING FOR DRAWINGS | ENGINEERING DRAWINGS COMPLETE | DATE TO FDOT FOR APPROVAL (If Required) | FDOT PERMIT APPROVAL | FKAA UTILITY PERMIT (Good for 1 year) | DATE TO CONTRACTOR FOR INSTALLA- TION | COMPLETE
16-01 | Central & US 1 | Hibiscus
16-02 | Tamarind Road & 7th Lane | Pamela Villa MM 102 Oceanside
16-03 | Tamarind Road & 4th Lane | Pamela Villa MM 102 Oceanside
16-04 | U.S. 1 & Lignumvitae Drive | Pamela Villa MM 102 Oceanside
16-05 | Mahogany Drive & Oleander Blvd. | Pamela Villa MM 102 Oceanside
16-06 | Collins Street & Village Drive | Angler's Park Shores MM 102.7 Ocean
16-07 | Sound Drive and Plante Street | Angler's Park Shores MM 102.7 Ocean
16-08 | Snapper Avenue & Blue Runner | Largo Sound Park MM 103.4 Ocean
16-09 | Kingfish Street & SE Marlin Avenue | Largo Sound Park MM 103.4 Ocean
16-10 | Barracuda Blvd & Turbot Street | Angler's Park MM 103.4 Ocean
16-11 | Dolphin Avenue & Turbot Street | Angler's Park MM 103.4 Ocean
16-12 | The end of Bonito Drive | Angler's Park MM 103.4 Ocean
16-13 | Largo Road & Big Pine Road
16-14 | Largo Road & Bahia Honda Road
16-15 | Largo Road & Vaca Road
`
FKAA 2016 | 08/19/15: PER MARNIE - THIS IS NOW AN FKAA PROJECT, and FKAA will only come back to the District if we request more hydrants than FKAA calculated.
FKAA-01 | Corner of Narragansett Lane and Boyd Drive | Bermuda Shores & Crosskey Wtrways | NO - FKAA (5 Year Plan)
FKAA-02 | Corner of Garden State Lane and Boyd Drive | Bermuda Shores & Crosskey Wtrways | NO - FKAA (5 Year Plan)
FKAA-03 | Corner of Oldsmar Lane and Boyd Drive | Bermuda Shores & Crosskey Wtrways | NO - FKAA (5 Year Plan)
FKAA-04 | Corner of Belmont Lane and Boyd Drive | Bermuda Shores & Crosskey Wtrways | NO - FKAA (5 Year Plan)
FKAA-05 | Corner of Canal Street and Botswick Drive | Bermuda Shores & Crosskey Wtrways | NO - FKAA (5 Year Plan)
FKAA-06 | Corner of Calder Road and Saratoga Lane | Bermuda Shores & Crosskey Wtrways | NO - FKAA (5 Year Plan)
FKAA-07 | Corner of Calder Road and Monmouth | Bermuda Shores & Crosskey Wtrways | NO - FKAA (5 Year Plan)
FKAA-08 | Corner of Bay Drive and Marlin Drive | Bermuda Shores & Crosskey Wtrways | NO - FKAA (5 Year Plan)
FKAA-09 | Corner of Bay Drive and Pompano Drive | Bermuda Shores & Crosskey Wtrways | NO - FKAA (5 Year Plan)
16-20 | Midway on Garden Cove Drive | Garden Cove | Not Feasible
16-21 | Corner of Pigeon Drive and Bunting Drive | Ocean Isles | Not Feasible
PHASE 4 15-01 | SEXTON COVE DRIVE AND SNIPE | Sexton Cove | Yes | FKAA | FKAA | N/A | N/A | NEW LOCATION | 2015-12-14 | COMPLETE 160418
15-02 | BUTTONWOOD CIRCLE AND OCEAN WAY Feasible on Ocean Way up to West side of Buttonwood then reduces to 4” water main | HARBOR SHORES | Yes | 150915 | Page 2 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160418
15-03 | FLORIDA DRIVE AND ROCK HARBOR DRIVE Feasible on Florida Drive ONLY | KEY LARGO PARK | Yes | 150915 | Page 3 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160603
15-04 | ROYAL PALM AND SILVER SPRINGS Feasible- 6” Water main on Both Streets | KEY LARGO PARK | Yes | 150915 | Page 4 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160603
15-05 | FLORIDA DRIVE AND ORANGE Feasible- 8” Water main on Florida and 6” water main on Orange LOCATION Needs to be on the right-side of the street | KEY LARGO PARK | Yes | 150915 | Page 5 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160603
15-06 | ROYAL PALM AND BUTTONWOOD DRIVE Feasible- 6” Water main on Both Streets | KEY LARGO PARK | Yes | 150915 | Page 6 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160603
15-07 | FLORIDA DRIVE AND ROYAL PALM Feasible- 8” on Florida ONLY - LOCATION Needs to be on the right-side of the street | KEY LARGO PARK | Yes | 150915 | Page 7 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160603
15-08 | LAKE SHORE DRIVE AND LAKE VIEW DRIVE Feasible- 6” on Lake Shore ONLY | KEY LARGO PARK | Yes | 150915 | Page 8 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160603
15-09 | SUNSET DRIVE AND ROCK HARBOR Feasible- 6” on Rock Harbor ONLY | KEY LARGO PARK | Yes | 150915 | Page 9 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160603
15-10 | MIAMI DRIVE (CENTER) Feasible- 6” on Miami | KEY LARGO PARK | Yes | 150915 | Page 10 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160614
15-11 | LAUDERDALE DRIVE AND WATERWAY DRIVE Feasible- 6” Water main on Both Streets | KEY LARGO PARK | Yes | 150915 | Page 11 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160603
15-12 | POINT PLEASANT DRIVE HALFWAY DOWN Feasible- 6” on Point Pleasant up to Unnamed Road (B38114 point Pleasant Drive) | POINT PLEASANT | Yes | 150915 | Page 12 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160614
15-13 | OCEAN BAY AND SUNSET OR BAY DRIVE Feasible- 6” on Ocean Bay Drive, NOT feasible on Sunset or Bay- 2” water mains | POINT PLEASANT | Yes | 150915 | Page 13 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160614
15-14 | SEXTON COVE DRIVE AND FLAMINGO | Sexton Cove | Yes | FKAA | FKAA | N/A | N/A | NEW LOCATION | 2015-12-14 | COMPLETE 160418
15-15 | OLEANDER AND ATLANTIC- New location for this hydrant feasible 8" water mains on both sides | MM 100 (Ocean) | Yes | 150915 | Page 15 | N/A | N/A | Approved | 2015-12-14 | COMPLETE 160614