## Sheet1
ACTION ITEM |  |  | DESIGNATES NEW ITEMS | TARGET
FROM MEETING | ASSIGNED TO | 2017 . . . ITEMS |  | DATE | STATUS | COMMENTS . . . For April 10, 2017 Meeting)
S.3 Controlling Finances | Beyer, Johnson | Quarterly Department Meeting (From Strategic Plan Controlling Finances) | The 1st Quarter Strategic Planning Meeting has been scheduled for 3/27/17. | 2016 (4th Qtr.) | Closed | Schedule 1st Quarter Strategic Planning meeting.
T.4 Identify Potential Legislation Important to District | Simmons | Identify Potential Legislation Important to District & Identify a District representative to represent the District, if/when required. | NEW: 1) From Strategic Planning Workshop 161114: Identify changes to legislation that formed the District that would not require voter approval. | 2017 (2nd Qtr.) changed from 1st Qtr.
| Thomas | Fire Hydrant Project Phase 5 (FY 2016-2017) | 170123 Installation of Phase 5 to begin within the next couple of weeks. | 2017 (2nd Qtr.) - changed from 1st Qtr. |  | 170406 Installation of the 1st 15 hydrants is completed, and drawing has been ordered for 16-16; 161214: BOCC approved ILA; 161212: The ILA has been submitted to Monroe County for approval at the 12/14/16 BOCC Meeting; 161114 The District approved the Contract, and the District is awaiting approval of the ILA with the County on 12/14/16 in order to begin installation; 161017 Selection of Vendor and Contract for RFP 17-001 scheduled for approval; 160919 The RFP 17-001 was submitted to the Board for approval, no response from FDOT; 160822 FKAA has not heard from FDOT, and the RFP will be submitted to the Board in September; 160712 FDOT received the paperwork for the Phase 5 hydrant that requires FDOT approval.
11/14/16 Meeting | Thomas | KLVAC & KLVFD Submit Governing Documents to the District in accordance with the contracts. |  | 2017 (1st Qtr.) |  | 170322 Documents have been submitted to the District; 170123 No documents have been submitted to the District.
O.4 & S.6 Limited Revenue Sources; Cost Recovery for the Fire Department & Corps | Simmons/Cullen/Bock | Review Cost Recovery Methods for the Fire Department & Corps; Review FL Statute 191 | 161212: Robinson/Garrido (What EMS charges can KLVFD bill)/Theron (Estimate to change legislation) : NEW From Strategic Planning Meeting 161114: 1) Review and Identify other medical services for which the Corps may possibly charge. 2) From Strategic Planning Meeting 161114: Review and Identify other services (extrication or supplies) for which the Fire Department may possibly charge. 3) From Strategic Planning Meeting 161114: Determine if the Fire Department may possibly charge non-residents for car accidents. | 2017 (2nd Qtr.) changed from 1st Qtr. |  | 161114: See newly-identified items from Strategic Planning Workshop; 161017: This item is being scheduled for 11/14/16 meeting; 160919 Three cost recovery items were combined into this item (and the other two are closed) & Theron will discuss at the next meeting; 160822 Commissioner Cullen approached FASD no responses were received; 160822 Theron will ensure Comm Cullen has appropriate legislation; 160725 This item was discussed at the 07/25 meeting was determined to be an ongoing item; 160720 Statute was changed to FS 191; 160627 Legal is reviewing.
O.3 Ensure Capital Improvement Funding | Thomas | Prepare ILA for Impact Fees. | Commissioner Thomas to discuss at meeting. | 2017 (2nd Qtr.) |  | 160725 Meeting with County scheduled for 08/22/16; 160627 Legal awaiting feedback from County as of 06/22/16.
O.3 Ensure Capital Improvement Funding | Thomas | Finalize Sales Tax ILA. | 161212 Commissioner Thomas would like to readdress in FY 17-18. | 2017 (2nd Qtr.) |  | 170120: District received executed ILA; 161214: BOCC approved ILA; 161212 Comm. Thomas would like to readdress in FY 17-18; 161017 The District will submit for BOCC approval at the 12/14/16 BOCC Mtg; 160919 The District approved the ILA from the County for 2017-2021; 160907 The County expects to send ILA to Smits in about a week; 160725 Meeting with County scheduled for 08/22/16; 160627 Legal is setting up meeting with County.
ACTION ITEM |  |  |  | TARGET
FROM MEETING | ASSIGNED TO | 2017 . . . ITEMS |  | DATE | STATUS
| Thomas | Fire Hydrant Project Phase 6 (FY 2017-2018) | 170322 The Phase 6 Drawings were ordered on 3/15/17; 161231 The drawings will be ordered the 1st quarter of 2017. | 2017 (1st Qtr.) |  | CONSTRUCTION CANNOT BEGIN PRIOR TO 10/1/17 . . . 170315 . . . Request to Engineer for drawings - need 4 more lactations; 161117 The Phase 6 Fire Hydrant Locations have been confirmed, and FKAA has confirmed no FDOT approval is required. The drawings will be ordered the 1st Qtr. of 2017. 160919 The Proposed Locations were submitted to FKAA to determine if the locations are feasible; 160822 The List is being submitted to FKAA.
S.3 Controlling Finances | Beyer, Johnson | Quarterly Department Meeting (From Strategic Plan Controlling Finances) |  | 2017 (1st Qtr.) |  | The 1st Qtr meeting was rescheduled for April 24, 2017.
T.2 Monitor the Economy | District Board | Review economic indicators and budget accordingly. |  | 2017 (2nd Qtr.) |  | Review during the budget process.
T.5 Maintain Awareness of Global Warming Issues | District Board | Maintain Awareness of Global Warming Issues |  | 2017 (2nd Qtr.) |  | Periodically review this item to identify if action is required.
T.3 Review Capital Budget | Johnson | Review and update the Five-Year Capital Improvement Plan annually. |  | 2017 (2nd Qtr.) |  | 160627 The Five-Year Capital Improvement Plan was updated and distributed to the Board on 4/25/16.
S.3 Controlling Finances | Beyer, Johnson | Quarterly Department Meeting (From Strategic Plan Controlling Finances) |  | 2017 (2nd Qtr.) |  | Schedule 2rd Quarter Strategic Planning meeting is scheduled for May 22, 2017.
| Fay | Draft Procedure 31-4, Acquisition & Disposition of Assets Purchased with Federal Funds |  | 2017 (2nd Qtr.)
W.2 & O.2 Create Guaranteed Staffing | Departments | Create Guaranteed Staffing by Creating retention incentives: Review salary increase, 401K and build advancement within the departments. | Review during budget process to determine if incentive is working. | 2017 (3rd Qtr.) |  | 2017: 160919 The District approved a Vacation Reimbursement Program for the Depts.; 160711 Guaranteed Staffing being reviewed during Budget Process.
W.2 & T.1 Create Guaranteed Staffing | Departments | Create Guaranteed Staffing by Minimizing loss of staffing: Develop and Expand the Core Group of Employees and Consider Increasing the millage. | Review during budget process to determine if incentive is working, and if the District should schedule another Firefighter I Class. | 2017 (3rd Qtr.) |  | 160906 The Firefighter I class started; 160711 Guaranteed Staffing being reviewed during Budget Process.
W.2 & W.1 Create Guaranteed Staffing | Departments | Create Guaranteed Staffing by Recruiting local volunteers: Calculate the cost of conducting Firefighter I training, and place advertising to encourage local volunteers. | Review during budget process to determine if advertising for volunteers was effective. | 2017 (3rd Qtr.) |  | 160902 The Department advertised for volunteers - there were no local volunteers; however, one Tavernier firefighter from Miami-Dade applied; 160711 Guaranteed Staffing being reviewed during Budget Process.
O.1 Cadet Program | Mirabella | Create a Cadet Program |  | 2017 (3rd Qtr.) |  | 160919 The Procedure was approved at this meeting and the details of the program will continue to be developed and will be presented to the Board in 2017; 160822 Draft Procedure submitted to Board; 160613 Commissioner Mirabella will revise the Cadet Program Procedure and resubmit to the Board.
| Thomas | Fire Hydrant Project Phase 7 (FY 2018-2019) |  | 2017 (3rd Qtr.) |  | CONSTRUCTION CANNOT BEGIN PRIOR TO 10/1/18
S.3 Controlling Finances | Beyer, Johnson | Quarterly Department Meeting (From Strategic Plan Controlling Finances) |  | 2017 (3rd Qtr.) |  | Schedule 4th Quarter Strategic Planning meeting.
SP: Property | District Board | Create Fire Training Grounds |  | Ongoing | Permission to Delete | The District Board will need to identify if this is a project they would like to pursue.
ACTION ITEM |  |  |  | TARGET
FROM MEETING | ASSIGNED TO | ONGOING ITEMS |  | DATE | STATUS
S.2 Community Support | Cullen, Bock | Community Support |  | 2016 Ongoing |  | 160523 The departments currently has an AED, CPR, Child Car Seat Installation and Address (residence/business) Verification Programs in place.
W.3 Improve Fractured Internal/External Communications | District Board & Staff | Identify when substantial staff time is required to research items. |  | 2016 Ongoing
W.3 Improve Fractured Internal/External Communications | District Board & Staff | Notify Clerk to disseminate information on issues of which the entire board should be aware. |  | 2016 Ongoing
W.3 Improve Fractured Internal/External Communications | Legal | Submit monthly legal report. |  | 2016 Ongoing
SP: Outreach | Fay | Update Website User Friendliness |  | 2016 Ongoing |  | 161200 and 170100: Extensive work on Commissioners & News Sections, Departments & Volunteers pages have been reviewed and updated (as required); 150506. Extensive work on Commissioners & News Sections; The Home, Commissioners, Schedule, News-Press, Volunteer pages have been reviewed and updated. All sections have been updated through 12/31/13. The website was reviewed in April, and numerous pages were slightly modified.
SP: Funding | Fay | Pursue additional grant funding |  | 2016 Ongoing |  | 170213: KLVFD applied for SAFER Grant; The Corps did not apply for a DOH Grant; 161117: KLVFD applied for AFG Grant; 161017 Grant to be submitted to Board for approval; 160919: The District will submit the upcoming AFG grant; 160822: 2015 AFG not received; 160627: 2016 DOH Grant. 160506: The District applied for the FP&S Grant; 160425 The District will apply for the FEMA FP&S Grant; 160323 The District applied for the DOH Grant; 160216 The Corps will apply for a DOH grant for training. 160118 The 2016 DOH Grant is being reviewed to determine if the District will submit a grant for the Corps. 160115 The District submitted the 2015 AFG Grant.
SP: Outreach | Fay | Create a Communications Plan Proposal for the District Board to consider Press Releases, Facebook & Twitter |  | 2016 Ongoing |  | 170102: Press Release District Accomplishments; 1090923: Fire Prevention Week Activities Press Release distributed; 160902: 911 Ceremony Press Release distributed; 160722: Trauma Star Press Release distributed; 150323: Press Releases were issued for Smoke Alarms and the KLVFD Call Volume; 150205 Press Release 2015 Accomplishments.
do not print below this area
ACTION ITEM |  |  |  | TARGET
FROM MEETING | ASSIGNED TO | 2016 . . . CLOSED ITEMS |  | DATE | STATUS
S.3 Controlling Finances | Beyer, Johnson | Quarterly Department Meeting (From Strategic Plan Controlling Finances) | . . . Quarterly Strategic Planning Meeting was conducted on 11/14/16. | 2016 (4th Qtr.) | Closed | 161114 The next proposed Strategic Planning Meeting is scheduled for 02/27/17; 160919 The next Strategic Planning Meeting is scheduled for 11/14/16; 160711 The Clerk will schedule a Department Workshop the 4th Qtr. of 2016.
O.3 Ensure Capital Improvement Funding | Thomas | Monitor and conduct communications with the County. |  | 2016 Ongoing | Closed | This item is closed - there are items for Impact Fees and Sales Tax ILA's with the county. 160725 Meeting with County scheduled for 08/22/16; 160627 Legal awaiting feedback from County as of 06/22/16.
O.4 Limited Revenue Sources | Cullen/Bock | Review Department Services to identify those items that are eligible to be billed. | . . . Perhaps these related items should be combined . . . | Closed | Closed | 160919 Item Combined with 160725 Limited Revenue Stream; 160822 No Action - Rescheduled for September 19, 2016 meeting.
O.5 ILA Impact | N/A | ILA Impact |  | Closed | Closed | Deleted and combined with Capital Funding.
O.5 ILA Impact | N/A | ILA Impact |  | Closed | Closed | Deleted and combined with Capital Funding.
S.1 Unity of District/Departments | Simmons | Unity of District/Departments |  | 2016-05-23 | Closed | 160523 This item was closed at the June 27th meeting.
S.3 Controlling Finances | Beyer, Johnson | Controlling Finances |  | 2016-06-27 | Closed | 160627 Commissioner Beyer & Johnson made a presentation to the Board. The Board will schedule a quarterly meeting.
S.4 Board Diversity | Thomas, Simmons | Board Diversity |  | 2016 | Closed | 160627 The Board closed this item at the June 27th meeting.
S.5 Training | Allen, Garrido | Training |  | 2016 (3rd Qtr.) | Closed | 160822 The Firefighter I program is awaiting approval from the State. This item is considered closed. 160725 This item was rescheduled for August 22nd meeting; Originally scheduled for July 25th Meeting.
S.6 EMS Cost Recovery | Cullen, Bock | EMS & Fire Cost Recovery | . . . Perhaps these related items should be combined . . . | Closed | Closed | 160919 Item Combined with 160725 Limited Revenue Stream; This item was discussed at the July 25th Meeting, and it was determined it would be an ongoing item.
S.7 Strong Volunteerism | Beyer | Strong Volunteerism |  | 2016 (3rd Qtr.) | Closed | 160919 Commissioner Beyer discussed the pro's and con's of the District's volunteer program.
SP: Outreach | Fay | Include in Communication Plan: Schedule Press Releases |  | 2014-03-31 | Closed | This item was combined into the Communications Plan Action Item.
W.4 Limited Revenue Sources | N/A | Limited Revenue Sources |  | Closed | Closed | Deleted and combined with Cost Recovery
DO NOT PRINT THIS AREA
|  | Create a Fire Hydrant Program - PHASE I . . . (2013 Hydrants) |  | 2014-07-01 | COMPLETED | PHASE 1: COMPLETE
| Legal | Prepare Mutual Aid Agreement with Ocean Reef. |  |  |  | Theron forwarded the Mutual Aid Agreement to Ocean Reef-it was Board approved on 10/20/14.
| Fay | Include in Communication Plan: Explore use of Social Media, Twitter & Facebook |  | 2014-03-31 | Closed | This item was combined into the Communications Plan Action Item.
130211 | Board/Legal | Finalize Mutual Aid Agreement with Islamorada Village. |  | 2014-10-01 | Closed | Islamorada Mutual Aid Agreement Approved September 15, 2014
|  | Resolve land ownership issues with old Fire Department & Resolve investing taxpayer money on land not owned by the District (These items were combined) as the end result will be the same for each item. |  | 2014-02-28 | Closed | 08/24/15 the District Board approved a Settlement with the Old Department.
|  | Create a Fire Hydrant Program - PHASE 2 . . . (2014 Hydrants) 15 Approved Hydrant Locations |  | 2014-07-01 | Closed | PHASE 2: The pads have been installed; 150910 There are three hydrants that need concrete pads installed; 150617 La Rocco started construction in Pirates Cove; 150508: La Rocco has the permits and may proceed with work; 150429: Comm. Beyer signed the permits; 150427; The Utility Permit should be issued this week; 150422: Phase 2 documents submitted to FKAA for Utility Permits. 150318 District is awaiting Certificate of Liability Insurance and Performance Bonds 150223: Board Selection of Vendor & LaRocco Contract; 150207 Bid Responses Due; 150106 Phase 2 RFP Issued.
|  | Prepare Mutual Aid Agreement with the County. |  | THE CHIEF WILL FOLLOWUP IN NOVEMBER | Closed | 150513 Pending receipt of original Agreements; 140424 Electronic copy of the Mutual Aid Agreement received; 150422 The Clerk requested a copy of the Mutual Aid Agreement on 3/19 & 4/22; 150318 The Agreement was approved at the 03/1815 BOCC Meeting; 02/23/15 District & County Mutual Aid Agreement to be approved at 02/23/15 District Meeting.
|  | Create a Communications Plan Proposal for the District Board to consider Press Releases, Facebook & Twitter |  | 2014-03-31 | Ongoing | 11/2/15 News Release District's 10th Anniversary; 10/27/15 Press Release Smoke Alarms; 09/18/15 Press Release Fire Prevention Week; 09/07/15 Press Release 911 Service; 50617 News Release for False Alarms completed and placed on hold as a change is required to the Ordinance; 150511 Issued News Release Open Burning; 03/09 Meeting Cancellation Notice; 02/20 District issued PR (Dave Gow); 1/15: District Issued Press Releases District Accomplishments & Fire Dept. issued Press Releases Training. 11/14: Issued Press Releases (Veterans Day); 10/14: Issued Press Releases for Fire Hydrant Project, Lake EMS Presentation, Smoke Alarm/Time Change. The 3/26 Meeting cancelled, 4/14/14 meeting plan submitted to Board, 5/12/14 Board Approved, and Facebook Account Established. The plan addresses Press Releases, Social Media (Facebook & Twitter) - 01/14: January Letter to the Editor; 02/06: Smoke Detector PR for Radio Stations; 03/00 Advertising (Newspaper/Radio) Press Releases; 04/00 Tanker Sale. 05/14 Press Release Sale of Tanker and Departments at Memorial Day & 4th of July Events. 07/14 Press Release District Awarded DHS/FEMA Grant for PPE. Facebook Messages are distributed weekly or bi-weekly. Radio & Newspaper issued for Press Releases for 911 Remembrance Event and Press Release for Fire Prevention Week & the Live-Burn Demonstration. Distributed PR information regarding Hydrant Project status (nice newspaper article in the Free Press. Issued PR and photo for the Fire Hydrant Project.
|  | Prepare Mutual Aid Agreement with Ocean Reef |  | 2016 | Closed | 160627: The Board approved the Mutual Aid Agreement on 16/06/27. Ocean Reef did not foresee any problems with the Mutual Aid Agreement, and the Ocean Reef Attorney is reviewing.
|  | Create a Fire Hydrant Program - PHASE 5 . . . (15 Hydrants) |  | FY 2016-2017 | Ongoing | PHASE 5: The Week of 160627 The Permit Application will be submitted to FKAA to begin FDOT approval; 160523 The Board approved the contract with Reynolds Engineering to prepare drawings at the 04/25/16 meeting; 160425 The Phase 5 List has been finalized; 160323 The List is currently being reviewed; 160125 KLVFD is identifying additional locations for Phase 5.
|  | Create a Fire Hydrant Program - PHASE 6 . . . (15 Hydrants) |  | FY 2017-2018 | Ongoing | PHASE 6: 160627 The hydrant locations are being identified.
SP: Money/Funding | Thomas | 304 Discretionary Sales Tax (Work with Monroe County) |  | IN PROCESS | I will delete. This is a duplicate from 2016 Strategic Planning Workshop. | 160622 Legal is awaiting feedback from the County; 160525: Legal will submit the District's new 5 Year Capital Investment Plan to the County; 160323: A meeting was held with the County the week of 03/21/16; 160218 Legal is setting up a meeting with the County. 160121 The District will begin coordinating the new FY 16/17 Sales Tax ILA.150914 The District will need to renegotiate a new 304 Discretionary Sales Tax ILA in 2016; 150427 The Board approved Amendment 1 to the ILA and it was sent on 4/29 for BOCC Approval at the 5/20 BOCC Meeting; 150427 Meeting Amendment to Sales Tax ILA for Wheaton's and Rowels completed in FY 14-15 rather than FY 13-14. District Legal worked with the County's Legal Department, and a 3 Year Inter-local Agreement was submitted to the BOCC for approval at their 8/20/14 Meeting. The District & BOCC approved 3 year ILA (2014-$250,000) (2015-$300,000) and (2016-$300,000)
SP: Money/Funding | Thomas | Impact Fees (Work with Monroe County) |  | IN PROCESS | I will delete. This is a duplicate from 2016 Strategic Planning Workshop. | 160623: Legal is awaiting feedback from the County; 160525: Legal is in discussion with the County; 160323: A meeting was held with the County the week of 03/21/16; 160218 Legal is setting up a meeting with the County. 160121 The District is coordinating the Impact Fee ILA with the County. 150915 Rosasco & Simmons will coordinate the new Impact Fee ILA. 140427: Chairman Thomas spoke with Roman and there is an estimated $10,000 of impact fees due to the District; 150413 Chairman Thomas spoke with County Administrator, and this item needs to be finalized with the County. The Chairman, Finance & Legal need to meet with the County regarding Impact Fees and prepare an Impact Fee ILA.
SP: Money | District Board | Legislature funding abilities |  | 2014-07-01 | I will delete. This is a duplicate from 2016 Strategic Planning Workshop. | See above.
SP: Money | Johnson | Create plan for building restoration, replacement fund & paving |  | 2014-07-01 | Ongoing | 160425: The revised Capital Improvement Plan was submitted to the Board on 04/25/16; 150910 Jennifer submitted the plan to the District and District Board. 150622 Jennifer is working with thee departments.150427, the 1st Draft of the Five-Year Capital Improvement Plan was distributed to Commissioners on 04//27/15.
SP: Money | Simmons | Create reserve fund categories |  | 2014-02-28 | I will delete. This is a duplicate from 2016 Strategic Planning Workshop. | 160523: Notices of Violation (False Alarm - Two) and (Open Burning - One) were issued.
SP: Money | Simmons | Research possibilities of special fees/assessments |  | 2014-07-01 | I will delete. This is a duplicate from 2016 Strategic Planning Workshop. | Special Assessment is discussed in the Legislative Funding Abilities Section.
SP: Staffing/Retention | Bock | Obtain and retain local volunteers for adequate staffing |  | 2014-07-01 | I will delete. This is a duplicate from 2016 Strategic Planning Workshop. | 160222: The Corps hired ten volunteers and three paid staff hired.
SP: Staffing/Retention | Bock | Track new staffing programs implemented in December 2013 |  | 2014-12-31 | I will delete. This is a duplicate from 2016 Strategic Planning Workshop. | Department management is reviewing and monitoring staff scheduling.
This Color relates to District Activities.
This color relates to Fire Hydrants.
This color: District Board direction is requested.
This color identifies Financial Items
130114 | KLVFD | AI 6.E. FASD recommends developing a Social Media Policy (Need Board Direction) |  |  | Complete
130508 | Bock | AI 10.A. Station #25 Door bell needs repair |  |  | Complete
130624 | Legal | 7.G. Review List of Bunker Gear List |  |  | Complete
130722 | Thomas | 7.B. Prepare Announcement for gov.deals.com for Old Squad 24 (5,000 Reserve) |  |  | Complete
130722 | Bock | Budget Workshop: Obtain Quotes from Hampson Insurance |  |  | Complete
130722 | KLVAC | Budget Workshop: Obtain Quotes from VFIS Insurance |  |  | Complete
130114 | Clerk | Budget Workshop: Obtain Revised Quote for Workman's Compensation |  |  | Complete
130114 | KLVFD | AI 5.C. Additional Website Information |  |  | 2012-07-16
130211 | Clerk | AI 11 Prepare list of Equipment for Commissioner Thomas (1 cent Infrastructure) |  |  | 2013-03-08
130114 | Beyer | AI 6.A. Forward Drug Testing Policies to Legal |  |  | 2013-03-31
130325 | Thomas | AI 4.A. New Estimate Station #'s |  |  | 2013-04-01
130114 | KLVAC | Bring Options Back to the Board |  |  | 2013-05-31
130408 | Mirabella | AI 11 Prepare list of Equipment for Commissioner Thomas (1 cent Infrastructure) |  |  | 2013-06-10
130408 | KLVAC | 9.B. Table Strategic Plan for 60 Days |  |  | 2013-07-01
130624 | KLVFD | 9.A. Start 401K |  |  | 2013-07-08
130708 | Allen | 6.A. Table Workman's Compensation to the next meeting |  |  | 2013-07-22
130211 | Thomas | 11. Fire Department Honor Guard will submit budget request |  |  | 2013-08-02
130422 | KLVAC | AI 11. VFIS Analysis of Insurance Policies |  |  | 297064
130508 | Mirabella | 4.C. Addendum to Contract |  |  | 406691
130508 | Legal | 7.F. Table the Pre-Construction Trip |  |  | 07/08/13
130114 | KLVFD (Newman) | 7.C. Extend Lease for Station 24 Property |  |  | 01/18/13
130114 | KLVFD (Newman) | AI 5.E. Apply for FP&S Grant |  |  | 01/28/13
130114 | KLVFD/KLVAC | AI 5.D. Distribute Accident Report to the Clerk for Commissioners |  |  | 01/28/13
130114 | Legal | AI 11. List of BOD Members to Clerk for distribution of District Items |  |  | 01/30/13
130114 | KLVFD/Legal/Clerk | AI 5.A. Finalize & Distribute Report to Governor's Office |  |  | 02/6/13
130114 | KLVFD (Newman) | AI 6.B. Notice of Violations (Legal w/ Griffeth & Clerk for setup) |  |  | 02/6/13
130114 | KLVAC | AI.6.D. 6 mos Credit Card Stmts to the Clerk for Commissioners |  |  | 02/6/13
130114 | KLVFD | AI 7.A. KLVAC Annual Report Report for 2012 is due in February |  |  | 03/7/13
130114 | KLVFD | AI 7.A. KLVFD Annual Report Report for 2011 is past due |  |  | 03/7/13
130211 | Mirabella | AI 7.A. KLVFD Annual Report Report for 2012 is due in February |  |  | 04/08/13
130708 | Thomas | AI 5.C.Strategic Plan |  |  | 0726/13
130624 | Mirabella | 7.C. Fire Hydrants - FKAA still needs drawings |  | 2014-03-08 | Closed
7.F. Host Community Event
|  | Pursue additional grant funding |  | 2014-03-31 | Ongoing | 160216 The Corps will apply for a DOH training grant. 160118 The 2016 DOH Grant is being reviewed to determine if the District will submit a grant for the Corps. 160115 The District submitted the 2015 AFG Grant. 150617 The FL DOH did not award the 2015 grant to the District for the generators; 150427 The District received the FEMA/DHS payment for the Bunker Gear grant; 150427 There were 11,400+ AFG Applications, and the District is one of 2770+ to receive peer review; 150415 AFG has begun to award the Dec 2014 AFG grants over the next 120 days. Good news, 150324 The FL DOH expects to award grants late May/June; 03/11 Submitted FL DOH Grant for Generators; 02/15 Reviewed FP&S for Department; 02/06/15 Reviewed SAFER Grant - KLVFD does not want to apply; 12/6/14 AFG Grant submitted ;On July 4th, the District was awarded the 2013 AFG Grant for PPE. 2/6/13 KLVFD Grant Submitted, Clerk reviewed grant requirements for DOH 2014 Grant (Corps) Due 2/28/14 & NVFC Training Grant (Fire Dept.) and provided information to the dept. 12/24/13 & 2/7/14. March review and prepare report for dept. for AFG Fire Prevention & Safety Grant.
SP: Staffing/Retention | Bock | Obtain and retain local volunteers for adequate staffing |  | 2014-07-01 | Ongoing | 16025 There were ten volunteers and three paid staff hired. 150824 The Departments have been testing and hiring new paramedics and firefighters. 150613 Testing was for new volunteers; 03/23: Four (4) firefighters were hired; 02/28 The Corps will conduct testing for paramedics on February 28th; 01/26/15 Corps (4) volunteers passed probation; 12/15/14 19 new firefighter candidates and17 passed the class; 11/21/14 ADVERTISING NEW VOLUNTEERS; TESTING ON 12/13/14. 12/13/14: 02/12 & 02/14 Reporter & Keynoter advertisements for FFI & FFII. Testing on February 22, 2014. 2/22: 20 Applicants tested. THE BOARD IS WAITING FOR REPORT FROM DEPT.
|  | Create a Fire Hydrant Program - PHASE 3 (2015 Hydrants) |  | FY 2015-2016 | COMPLETE | PHASE 3: 160212 Phase 3 is completed. 160121 Installation to begin for the last Phase 3 8 hydrants 01/21/16.151109 Fire Hydrants NOW require Monroe County permits - This is new to the process. La Rocco will obtain prior to starting work; 151021 FKAA Permits have been issued and returned to FKAA; This is an FYI 14-15 Project 140422: These will be submitted150223: Board Selection of Vendor & LaRocco Contract; 150207 Bid Responses Due; 150106 Phase 2 RFP Issued;
SP: Property | Garrido | Create a Fire Hydrant Program - PHASE 4 . . . (15 Hydrants) |  | FY 2015-2016 | Closed 160614 | PHASE 4: This Phase was officially closed on 160614; 160523 Installation of the nine (9) hydrants in Key Largo Park is scheduled to begin on 05/24/16; 160425 Three hydrant locations have been completed; 160323 Hydrants are being installed and Permits Issued Except for 2 the two Sexton Cove hydrants moved to Phase 4; 160218 Pending Permit signatures. 160121 Installation will begin when Phase 3 is completed. A fire hydrant is needed at Central & US 1, and it will be added to Phase 5. 151214 The District Board Approved the Selection of the Vendor and the Contract with La Rocco. 151111 Drawings have been completed, and the RFP was released on 11/9/15; 150910 Two hydrant locations are being confirmed. Battalion Chief Griffeths would like to see Cross-Keys Waterway sub-division moved to a higher priority. Commissioner Thomas conducted preliminary discussions with FKAA, and 9 hydrants are being placed on the FKAA Five (5) Year Master Plan. For the locations, see the Master Fire Hydrant List (Bermuda Shores and Cross-Key Waterways Sub-division).
| Legal | Prepare Mutual Aid Agreement with Miami Dade. |  | 2016 Ongoing |  | 161107 Pending a change to the signature page; 161017 The Board approved the Agreement; 160919 Agreement was submitted to Miami Dade; 160627: Legal submitted the Mutual Aid Agreement to Miami Dade; 160523 Per Chief Bock, Miami-Dade needs a copy of the Mutual Aid Agreement; 160121 Per Chief Bock the Miami Dade Review process takes approximately 1 year to complete. 150511: The agreement needs to be approved by Miami Dade's Fire Chief, MDFR Legal, the MD County Administrator, MD County Legal & then it goes to the Miami Dade County Commissioners. Any changes will have to be approved as well. 150223 & 150126: The Mutual Aid Agreement has been submitted to Miami-Dade Legal for review.